## Sheet1
Work Breakdown Structure (WBS)
Task-ID | Task | Sub-Tasks | Assigned Team Member | Prority | Deadline
1 | Venue Setup | Secure venue | Logistic Team | High | one week
|  | Organize equipment | Logistic Team | High | one week
|  | Ensure seating and stages arrangments | Logistic Team | Medium | three days
2 | Sponser and mentoring | Talk with sponsers | Sponsership Team | High | one month
|  | Confirm agreements | Sponsership Team | High | four weeks
|  | Schedual events | Sponsership Team | Medium | one week
3 | Registration | Make registration Link | Registration Team | High | three weeks
|  | Confirm registration | Registration Team | High | three weeks
|  | Send registration confirmation | Registration Team | Low | three weeks
|  | Send Event details (Start date, End date) | Registration Team | Medium | three days
|  | Send timeline details for the event | Registration Team | Medium | one day
5 | Event Scheduallling | Plan workshops and sessions | Program Team | High | two weeks
|  | Publish final scheduale | Program Team | Medium | one week
6 | After event | Gather feedback | Marketing Team | High | after event
|  | Clear venue | Marketing Team | Medium | after event
|  | Share highlights with sponsers | Marketing Team | Medium | after event
|  | Post videos and photos on social media | Marketing Team | Medium | after event
|  | Post feedback on social media | Marketing Team | Low | after event
|  | Finalize payments to vendors | Finanical Team | High | after event
|  |  | Assigned Team Member |  | Prority
|  |  | Logistic Team |  | Low
|  |  | Sponsership Team |  | Medium
|  |  | Registration Team |  | High
Program Team
Marketing Team
Finanical Team
Note on C19: Bassel: