## Sheet1
Task_ID | Task | Dependancy | Start Date | End Date | Duration | Status | %Done
1 | Research and Secure Venue | None | 2024-02-01 | 2024-02-25 | 24 | Completed
2 | Sponsor Agreements | None | 2024-02-01 | 2024-03-04 | 32 | In Progress
3 | Develop Marketing Materials | Sponser Agreements | 2024-02-08 | 2024-03-11 | 32 | In Progress
4 | Open Participant Registration | None | 2024-02-15 | 2024-03-18 | 32 | In Progress
5 | Confirm Event Agenda | None | 2024-02-15 | 2024-03-11 | 25 | In Progress
6 | Recruit Mentors | Confirm Event Agenda | 2024-02-22 | 2024-03-18 | 25 | In Progress
7 | Venue Setup | Research and Secure Venue | 2024-03-21 | 2024-03-23 | 2 | To Do
8 | Event Execution | Venue Setup | 2024-03-21 | 2024-03-23 | 2 | To Do
9 | Post-event Wrap-up | Event Day | 2024-03-24 | 2024-04-01 | 8 | To Do
Statuses
To Do
In Progress
Blocked
Completed